## Overview
SEMAT Alpha State Overview
Stakeholders |  | Opportunity
Recognized | 0/3 | Identified | 0/3
Represented | 0/4 | Solution Needed | 0/5
Involved | 0/3 | Value Established | 0/5
In Agreement | 0/5 | Viable | 0/6
Satisfied for Deployment | 0/2 | Addressed | 0/3
Satisfied in Use | 0/2 | Benefit Accrued | 0/2
Requirements |  | Software System
Conceived | 0/4 | Architecture Selected | 0/6
Bounded | 0/9 | Demonstrable | 0/6
Coherent | 0/9 | Useable | 0/7
Acceptable | 0/5 | Ready | 0/4
Addressed | 0/4 | Operational | 0/3
Fulfilled | 0/3 | Retired | 0/4
Work |  | Way of Working |  | Team
Initiated | 0/7 | Principles Established | 0/6 | Seeded | 0/11
Prepared | 0/12 | Foundation Established | 0/6 | Formed | 0/10
Started | 0/4 | In Use | 0/6 | Collaborating | 0/4
Under Control | 0/7 | In Place | 0/3 | Performing | 0/5
Concluded | 0/3 | Working Well | 0/4 | Adjourned | 0/3
Closed | 0/6 | Retired | 0/2
Version 1.0 - 2014

## Stakeholders
Stakeholders | Back to Overview
Recognized | All the different groups of stakeholders that are, or will be, affected by the development and operation of the software system are identified. | FALSE
| There is agreement on the stakeholder groups to be represented. At a minimum, the stakeholders groups that fund, use, support, and maintain the system have been considered. | FALSE
| The responsibilities of the stakeholder representatives have been defined. | FALSE
Represented | The stakeholder representatives have agreed to take on their responsibilities. | FALSE
| The stakeholder representatives are authorized to carry out their responsibilities. | FALSE
| The collaboration approach among the stakeholder representatives has been agreed. | FALSE
| The stakeholder representatives support and respect the team's way of working. | FALSE
Involved | The stakeholder representatives assist the team in accordance with their responsibilities. | FALSE
| The stakeholder representatives provide feedback and take part in decision making in a timely manner. | FALSE
| The stakeholder representatives promptly communicate changes that are relevant for their stakeholder groups. | FALSE
In Agreement | The stakeholder representatives have agreed upon their minimal expectations for the next deployment of the new system. | FALSE
| The stakeholder representatives are happy with their involvement in the work. | FALSE
| The stakeholder representatives agree that their input is valued by the team and treated with respect. | FALSE
| The team members agree that their input is valued by the stakeholder representatives and treated with respect. | FALSE
| The stakeholder representatives agree with how their different priorities and perspectives are being balanced to provide a clear direction for the team. | FALSE
Satisfied for Deployment | The stakeholder representatives provide feedback on the system from their stakeholder group perspective. | FALSE
| The stakeholder representatives confirm that they agree that the system is ready for deployment. | FALSE
Satisfied in Use | Stakeholders are using the new system and providing feedback on their experiences. | FALSE
| The stakeholders confirm that the new system meets their expectations. | FALSE

## Opportunity
Opportunity | Back to Overview
Identified | An idea for a way of improving current ways of working, increasing market share or applying a new or innovative software system has been identified. | FALSE
| At least one of the stakeholders wishes to make an investment in better understanding the opportunity and the value associated with addressing it. | FALSE
| The other stakeholders who share the opportunity have been identified. | FALSE
Solution Needed | The stakeholders in the opportunity and the proposed solution have been identified. | FALSE
| The stakeholders' needs that generate the opportunity have been established. | FALSE
| Any underlying problems and their root causes have been identified. | FALSE
| It has been confirmed that a software-based solution is needed. | FALSE
| At least one software-based solution has been proposed. | FALSE
Value Established | The value of addressing the opportunity has been quantified either in absolute terms or in returns or savings per time period (e.g. per annum). | FALSE
| The impact of the solution on the stakeholders is understood. | FALSE
| The value that the software system offers to the stakeholders that fund and use the software system is understood. | FALSE
| The success criteria by which the deployment of the software system is to be judged are clear. | FALSE
| The desired outcomes required of the solution are clear and quantified. | FALSE
Viable | A solution has been outlined. | FALSE
| The indications are that the solution can be developed and deployed within constraints. | FALSE
| The risks associated with the solution are acceptable and manageable. | FALSE
| The indicative (ball-park) costs of the solution are less than the anticipated value of the opportunity. | FALSE
| The reasons for the development of a software-based solution are understood by all members of the team. | FALSE
| It is clear that the pursuit of the opportunity is viable. | FALSE
Addressed | A usable system that demonstrably addresses the opportunity is available. | FALSE
| The stakeholders agree that the available solution is worth deploying. | FALSE
| The stakeholders are satisfied that the solution produced addresses the opportunity. | FALSE
Benefit Accrued | The solution has started to accrue benefits for the stakeholders. | FALSE
| The return-on-investment profile is at least as good as anticipated. | FALSE

## Requirements
Requirements | Back to Overview
Conceived | The initial set of stakeholders agrees that a system is to be produced. | FALSE
| The stakeholders that will use the new system are identified. | FALSE
| The stakeholders that will fund the initial work on the new system are identified. | FALSE
| There is a clear opportunity for the new system to address. | FALSE
Bounded | The stakeholders involved in developing the new system are identified. | FALSE
| The stakeholders agree on the purpose of the new system. | FALSE
| It is clear what success is for the new system. | FALSE
| The stakeholders have a shared understanding of the extent of the proposed solution. | FALSE
| The way the requirements will be described is agreed upon. | FALSE
| The mechanisms for managing the requirements are in place. | FALSE
| The prioritization scheme is clear. | FALSE
| Constraints are identified and considered. | FALSE
| Assumptions are clearly stated. | FALSE
Coherent | The requirements are captured and shared with the team and the stakeholders. | FALSE
| The origin of the requirements is clear. | FALSE
| The rationale behind the requirements is clear. | FALSE
| Conflicting requirements are identified and attended to. | FALSE
| The requirements communicate the essential characteristics of the system to be delivered. | FALSE
| The most important usage scenarios for the system can be explained. | FALSE
| The priority of the requirements is clear. | FALSE
| The impact of implementing the requirements is understood. | FALSE
| The team understands what has to be delivered and agrees to deliver it. | FALSE
Acceptable | The stakeholders accept that the requirements describe an acceptable solution. | FALSE
| The rate of change to the agreed requirements is relatively low and under control. | FALSE
| The value provided by implementing the requirements is clear. | FALSE
| The parts of the opportunity satisfied by the requirements are clear. | FALSE
| The requirements are testable. | FALSE
Addressed | Enough of the requirements are addressed for the resulting system to be acceptable to the stakeholders. | FALSE
| The stakeholders accept the requirements as accurately reflecting what the system does and does not do. | FALSE
| The set of requirement items implemented provide clear value to the stakeholders. | FALSE
| The system implementing the requirements is accepted by the stakeholders as worth making operational. | FALSE
Fulfilled | The stakeholders accept the requirements as accurately capturing what they require to fully satisfy the need for a new system. | FALSE
| There are no outstanding requirement items preventing the system from being accepted as fully satisfying the requirements. | FALSE
| The system is accepted by the stakeholders as fully satisfying the requirements. | FALSE

## Software System
Software System | Back to Overview
Architecture Selected | The criteria to be used when selecting the architecture have been agreed on. | FALSE
| Hardware platforms have been identified. | FALSE
| Programming languages and technologies to be used have been selected. | FALSE
| System boundary is known. | FALSE
| Significant decisions about the organization of the system have been made. | FALSE
| Buy, build and reuse decisions have been made. | FALSE
Demonstrable | Key architectural characteristics have been demonstrated. | FALSE
| The system can be exercised and its performance can be measured. | FALSE
| Critical hardware configurations have been demonstrated. | FALSE
| Critical interfaces have been demonstrated. | FALSE
| The integration with other existing systems has been demonstrated. | FALSE
| The relevant stakeholders agree that the demonstrated architecture is appropriate. | FALSE
Usable | The system can be operated by stakeholders who use it. | FALSE
| The functionality provided by the system has been tested. | FALSE
| The performance of the system is acceptable to the stakeholders. | FALSE
| Defect levels are acceptable to the stakeholders. | FALSE
| The system is fully documented. | FALSE
| Release content is known. | FALSE
| The added value provided by the system is clear. | FALSE
Ready | Installation and other user documentation are available. | FALSE
| The stakeholder representatives accept the system as fit-for-purpose. | FALSE
| The stakeholder representatives want to make the system operational. | FALSE
| Operational support is in place. | FALSE
Operational | The system has been made available to the stakeholders intended to use it. | FALSE
| At least one example of the system is fully operational. | FALSE
| The system is fully supported to the agreed service levels. | FALSE
Retired | The system has been replaced or discontinued. | FALSE
| The system is no longer supported. | FALSE
| There are no “official” stakeholders who still use the system. | FALSE
| Updates to the system will no longer be produced. | FALSE

## Work
Work | Back to Overview
Initiated | The result required of the work being initiated is clear. | FALSE
| Any constraints on the work’s performance are clearly identified. | FALSE
| The stakeholders that will fund the work are known. | FALSE
| The initiator of the work is clearly identified. | FALSE
| The stakeholders that will accept the results are known. | FALSE
| The source of funding is clear. | FALSE
| The priority of the work is clear. | FALSE
Prepared | Commitment is made. | FALSE
| Cost and effort of the work are estimated. | FALSE
| Resource availability is understood. | FALSE
| Governance policies and procedures are clear. | FALSE
| Risk exposure is understood. | FALSE
| Acceptance criteria are defined and agreed with client. | FALSE
| The work is broken down sufficiently for productive work to start. | FALSE
| Tasks have been identified and prioritized by the team and stakeholders. | FALSE
| A credible plan is in place. | FALSE
| Funding to start the work is in place. | FALSE
| The team or at least some of the team members are ready to start the work. | FALSE
| Integration and delivery points are defined. | FALSE
Started | Development work has been started. | FALSE
| Work progress is monitored. | FALSE
| The work is being broken down into actionable work items with clear definitions of done. | FALSE
| Team members are accepting and progressing tasks. | FALSE
Under Control | Tasks are being completed. | FALSE
| Unplanned work is under control. | FALSE
| Risks are under control as the impact if they occur and the likelihood of them occurring have been reduced to acceptable levels. | FALSE
| Estimates are revised to reflect the team’s performance. | FALSE
| Measures are available to show progress and velocity. | FALSE
| Re-work is under control. | FALSE
| Tasks are consistently completed on time and within their estimates. | FALSE
Concluded | All outstanding tasks are administrative housekeeping or related to preparing the next piece of work. | FALSE
| Work results have been achieved. | FALSE
| The stakeholder(s) has accepted the resulting software system. | FALSE
Closed | Lessons learned have been itemized, recorded and discussed. | FALSE
| Metrics have been made available. | FALSE
| Everything has been archived. | FALSE
| The budget has been reconciled and closed. | FALSE
| The team has been released. | FALSE
| There are no outstanding, uncompleted tasks. | FALSE

## Way of Working
Way of Working | Back to Overview
Principles Established | Principles and constraints are committed to by the team. | FALSE
| Principles and constraints are agreed to by the stakeholders. | FALSE
| The tool needs of the work and its stakeholders are agreed. | FALSE
| A recommendation for the approach to be taken is available. | FALSE
| The context within which the team will operate is understood. | FALSE
| The constraints that apply to the selection, acquisition and use of practices and tools are known. | FALSE
Foundation Established | The key practices and tools that form the foundation of the way-of-working are selected. | FALSE
| Enough practices for work to start are agreed to by the team. | FALSE
| All non-negotiable practices and tools have been identified. | FALSE
| The gaps that exist between the practices and tools that are needed and the practices and tools that are available have been analyzed and understood. | FALSE
| The capability gaps that exist between what is needed to execute the desired way of working and the capability levels of the team have been analyzed and understood. | FALSE
| The selected practices and tools have been integrated to form a usable way-of-working. | FALSE
In Use | The practices and tools are being used to do real work. | FALSE
| The use of the practices and tools selected are regularly inspected. | FALSE
| The practices and tools are being adapted to the team’s context. | FALSE
| The use of the practices and tools is supported by the team. | FALSE
| Procedures are in place to handle feedback on the team’s way of working. | FALSE
| The practices and tools support team communication and collaboration. | FALSE
In Place | The practices and tools are being used by the whole team to perform their work. | FALSE
| All team members have access to the practices and tools required to do their work. | FALSE
| The whole team is involved in the inspection and adaptation of the way-of-working. | FALSE
Working well | Team members are making progress as planned by using and adapting the way-of-working to suit their current context. | FALSE
| The team naturally applies the practices without thinking about them | FALSE
| The tools naturally support the way that the team works. | FALSE
| The team continually tunes their use of the practices and tools. | FALSE
Retired | The team's way of working is no longer being used. | FALSE
| Lessons learned are shared for future use. | FALSE

## Team
Team | Back to Overview
Seeded | The team mission has been defined in terms of the opportunities and outcomes. | FALSE
| Constraints on the team's operation are known. | FALSE
| Mechanisms to grow the team are in place. | FALSE
| The composition of the team is defined. | FALSE
| Any constraints on where and how the work is carried out are defined. | FALSE
| The team's responsibilities are outlined. | FALSE
| The level of team commitment is clear. | FALSE
| Required competencies are identified. | FALSE
| The team size is determined. | FALSE
| Governance rules are defined. | FALSE
| Leadership model is selected. | FALSE
Formed | Individual responsibilities are understood. | FALSE
| Enough team members have been recruited to enable the work to progress. | FALSE
| Every team member understands how the team is organized and what their individual role is. | FALSE
| All team members understand how to perform their work. | FALSE
| The team members have met (perhaps virtually) and are beginning to get to know each other | FALSE
| The team members understand their responsibilities and how they align with their competencies. | FALSE
| Team members are accepting work. | FALSE
| Any external collaborators (organizations, teams and individuals) are identified. | FALSE
| Team communication mechanisms have been defined. | FALSE
| Each team member commits to working on the team as defined. | FALSE
Collaborating | The team is working as one cohesive unit. | FALSE
| Communication within the team is open and honest. | FALSE
| The team is focused on achieving the team mission. | FALSE
| The team members know each other. | FALSE
Performing | The team consistently meets its commitments. | FALSE
| The team continuously adapts to the changing context. | FALSE
| The team identifies and addresses problems without outside help. | FALSE
| Effective progress is being achieved with minimal avoidable backtracking and reworking. | FALSE
| Wasted work, and the potential for wasted work are continuously eliminated. | FALSE
Adjourned | The team responsibilities have been handed over or fulfilled. | FALSE
| The team members are available for assignment to other teams. | FALSE
| No further effort is being put in by the team to complete the mission. | FALSE